## Langkah Detail Pelaksanaan
KEGIATAN 7: LANGKAH-LANGKAH DETAIL PELAKSANAAN
Pengkodean Modul Manajemen Stok, Produksi, & Distribusi E-SCM Marmer Tulungagung
No | Tahapan Langkah Kerja | Yang Dilakukan | Yang Harus Disiapkan | Output Deliverable
1 | Langkah 1 — Setup Environment | Pilih Laravel 11 PHP 8.3 & Tailwind CSS, install Composer, Node.js, Git. | Spesifikasi teknis, akses development. | Environment siap pakai, Git repo terinisialisasi.
2 | Langkah 2 — Struktur Project MVC | Buat struktur folder arsitektur MVC sesuai standar Laravel 11. | Environment langkah 1. | Boilerplate MVC siap diisi fitur (IMG-7.1).
3 | Langkah 3 — Modul Manajemen Stok | Bangun CRUD bahan baku marmer, grade, mutasi in/out strict integer. | Skema DB (Keg 4), mockup UI (Keg 6). | Modul stok berfungsi live (IMG-7.2).
4 | Langkah 4 — Modul Produksi Kanban | Bangun penerbitan SPK, pantau 7 mesin bubut, perpindahan stage Kanban. | Skema DB produksi, mockup UI. | Modul produksi Kanban berfungsi (IMG-7.3).
5 | Langkah 5 — Modul Distribusi & QC | Bangun form QC 2 tahap, log residu tatal marmer, checklist packing kayu. | Skema DB distribusi & QC. | Modul distribusi & QC live (IMG-7.4 s.d. 7.6).
6 | Langkah 6 — Autentikasi RBAC | Bangun login multi-role (8 peran), middleware akses, proteksi CSRF. | Daftar peran dari Kegiatan 3. | Matriks otorisasi RBAC aktif (Form 7.3).
7 | Langkah 7 — Unit Testing Modul | Uji fungsi secara terpisah via PHPUnit (72 tests, 376 assertions). | Daftar fungsi uji, data empiris. | Unit test 100% PASS tanpa error.
8 | Langkah 8 — Code Review & Docs | Review PSR-12, clean code, dokumentasi README & Swagger API. | Source code langkah 3-7. | Checklist PSR-12 patuh (Form 7.4).

## Form 7.1 - Checklist Modul
FORMULIR 7.1: CHECKLIST PENGEMBANGAN MODUL APLIKASI
No | Modul Sistem | Fitur Utama yang Dikembangkan | Pengembang | Selesai | Status
1 | Bahan Baku | CRUD bongkahan batu, filter grade, alert stok kritis, log mutasi | Tim Backend | 20 Agt | 100% SELESAI
2 | Produksi SPK | Penerbitan SPK, monitoring 7 mesin bubut, Kanban board | Backend & UI | 21 Agt | 100% SELESAI
3 | Quality Control | Form inspeksi QC1 & QC2 kilap > 95 GU, approval lolos | QA & Backend | 21 Agt | 100% SELESAI
4 | Residu Limbah | Logging residu tatal marmer, akumulasi kerajinan teraso | Tim Backend | 22 Agt | 100% SELESAI
5 | Distribusi | Checklist packing kayu solid, Surat Jalan, tracking live | Fullstack | 22 Agt | 100% SELESAI
6 | Katalog Publik | Etalase wastafel/lantai, search, detail, konsultasi WA | Tim Frontend | 22 Agt | 100% SELESAI
7 | Checkout Bayar | Direct checkout DP 50%/100%, invoice QRIS otomatis | Fullstack | 23 Agt | 100% SELESAI
8 | Pesanan Masuk | Panel admin verifikasi transfer, konversi SPK otomatis | Tim Backend | 23 Agt | 100% SELESAI
9 | Auth RBAC | Middleware auth multi-role (8 peran), proteksi CSRF | Tim Keamanan | 23 Agt | 100% SELESAI

## Form 7.2 - Verifikasi Rute
FORMULIR 7.2: VERIFIKASI 36 RUTE HTTP & CONTROLLER
Grup Rute | Jumlah | Controller Utama | Middleware Keamanan | Status Verifikasi
Publik & Katalog | 6 Rute | CatalogController, CheckoutController | Guest / Rate Limiter (60/min) | 100% PASS
Bahan Baku & Stok | 5 Rute | MaterialController, InventoryController | auth, role:gudang,owner | 100% PASS
Produksi & Kanban | 6 Rute | ProductionOrderController | auth, role:mandor,owner | 100% PASS
QC & Residu Limbah | 6 Rute | QCInspectionController, WasteLogController | auth, role:qc,mandor | 100% PASS
Distribusi Logistik | 5 Rute | ShipmentController, TrackingController | auth, role:distribusi,owner | 100% PASS
Orders & Admin | 5 Rute | OrderAdminController, DashboardController | auth, role:admin,owner | 100% PASS
AI Forecasting | 3 Rute | ForecastingController | auth, role:owner,admin | 100% PASS

## Form 7.3 - Matriks RBAC CRUD
FORMULIR 7.3: MATRIKS OTORISASI HAK AKSES RBAC 8 PERAN (CRUD MATRIX)
Peran (Role) | Bahan Baku | SPK Kanban | Quality Control | Residu Limbah | Distribusi | Admin Orders | AI Forecast
Owner / Pimpinan | CRUD / View | CRUD / View | View / Approve | View / Export | View / Export | Full Access | Full Access
Petugas Gudang | CRUD | View | No Access | View | No Access | No Access | View
Mandor Produksi | View / Deduct | CRUD (Kanban) | View | Create Scrap | No Access | No Access | No Access
Petugas QC | No Access | View | CRUD Inspeksi | Create | View | No Access | No Access
Supir Distribusi | No Access | No Access | No Access | No Access | Update Live | No Access | No Access
Petugas Limbah | No Access | No Access | No Access | CRUD | No Access | No Access | No Access
Admin Pesanan | View | Create SPK | View | No Access | Create SJ | CRUD Orders | View
Pembeli Publik | No Access | No Access | No Access | No Access | View Track | No Access | No Access

## Form 7.4 - Kepatuhan PSR-12
FORMULIR 7.4: CHECKLIST KEPATUHAN STANDAR KODE PSR-12 & CLEAN CODE
Aspek Standar Kode | Deskripsi Aturan / Best Practice | Tool Evaluasi | Hasil Audit Kode | Status
Format Standar PHP | Kepatuhan PSR-12 (Indentation 4 spasi, typehint, namespace) | PHP_CodeSniffer | 0 Error / 0 Warning | COMPLIANT
Type Safety | Deklarasi return type dan parameter typing pada seluruh Controller | PHPStan Level 6 | 100% Strict Type | COMPLIANT
Dependency Injection | Penggunaan Service Layer dan Constructor Injection | Architecture Review | Decoupled Clean Code | COMPLIANT
Keamanan Query | Menggunakan Eloquent ORM & Parameterized Binding | Laravel Security Audit | Anti-SQL Injection | SECURE